## Piling
Row | Event Component / Parameter | Forecast A (BAU Risk) | Forecast B (Lean-Optimized) | Remarks / Logic
2 | Total Piles | 413.3333 | 413.3333 | Derived from 487 RMT / 0.9m spacing
3 | Shift Duration (mins) | 540 | 540 | Standard working shift
4 | Concurrency Index | 1.66 | 1.66 | Historical site parallel tracking
5 | Rig Positioning | 35 | 24.5 | Forecast B = Forecast A * 0.70 (VSM)
6 | Boring (0-8m Soil) | 55 | 55 | Value-Adding (Unchanged)
7 | Boring (8-18m Rock) | 125 | 125 | Value-Adding (Unchanged)
8 | Cleaning & Flushing | 40 | 28 | Forecast B = Forecast A * 0.70 (VSM)
9 | Cage Lowering | 45 | 31.5 | Forecast B = Forecast A * 0.70 (VSM)
10 | RMC Wait Lag | 90 | 36 | Forecast B strictly targets 36 mins (JIT)
11 | Concreting (9.14m3) | 65 | 65 | Value-Adding (Unchanged)
12 | Rig Shifting | 40 | 28 | Forecast B = Forecast A * 0.70 (VSM)
13 | Total Cycle Time (mins) | 495 | 393 | Sum of sub-activities
14 | Uncrashed Piles / Day | 1.8109 | 2.2809 | Shift / Cycle * Concurrency (Breaks loop)
15 | Uncrashed Total Days | 228.2463 | 181.2137 | Total Piles / Uncrashed Piles per Day
16 | Parallel Scaling Lever | 1 | 0.85 | 0.85 applies for concurrent twin-rig CPM crashing
17 | Final Total Days | 228.2463 | 154.0317 | Applies Lean timeline crash (Breaks loop)
18 | Effective Piles / Day | 1.8109 | 2.6834 | Total Piles / Final Days (For reporting)
19 | Working Fuel (L) | 38646.6667 | 35236.6667 | Constant physical work energy
20 | Idle Fuel (L) | 6045 | 3022.5 | Uses exact formula: (Piles*(Cage+Wait)/60)*6.5
21 | Fixed Electricity (Tonnes) | 0.54 | 0.54 | Standard site overhead
22 | Total Carbon (Tonnes) | 120.3137 | 103.0746 | Converts Liters to Tonnes CO2e + Electricity

## Excavation
Row | Volume Derivation Parameter | Value | Formula Logic | Remarks
2 | Total Plot Area (m²) | 8415 |  | Given project configuration
3 | Basement Coverage Factor | 0.85 |  | Standard urban plot coverage
4 | Effective Footprint (m²) | 7152.75 | 7152.75 | Plot Area * Coverage Factor
5 | Number of Basements | 3 |  | Given project configuration
6 | Height per Basement (m) | 3.5 |  | Standard floor-to-floor height
7 | Raft/Pile Cap Allowance (m) | 2.5 |  | Foundation mat clearance
8 | Total Depth (m) | 13 | 13 | (Basements * Height) + Allowance
9 | Total Excavation Volume (m³) | 92985.75 | 92985.75 | Effective Footprint * Total Depth
Row | Event Component / Parameter | Forecast A (BAU Risk) | Forecast B (Lean-Optimized) | Remarks / Logic
12 | Excavation Volume (m³) | 92985.75 | 92985.75 | Linked directly to derivation in Row 9
13 | Soil Stratum Ratio | 0.35 | 0.35 | Historical site strata analysis (35%)
14 | Hard Rock Stratum Ratio | 0.65 | 0.65 | Historical site strata analysis (65%)
15 | Soil Volume (m³) | 32545.0125 | 32545.0125 | Total Volume * Soil Ratio
16 | Rock Volume (m³) | 60440.7375 | 60440.7375 | Total Volume * Rock Ratio
17 | Tipper Capacity (m³/trip) | 10 | 10 | Standard volumetric capacity
18 | Total Required Trips | 9298.575 | 9298.575 | Total Volume / Capacity
19 | Shift Duration (mins) | 540 | 540 | Standard working shift
20 | Excavator Fleet Size | 2 | 2 | Standard concurrent mass excavation fleet
21 | Inbound Positioning (mins) | 8 | 1 | Forecast B = 1.0 (VSM Haul Route Leveling)
22 | Shovel Loading Time (mins) | 6 | 6 | Value-Adding (Unchanged)
23 | Outbound Positioning (mins) | 10 | 1 | Forecast B = 1.0 (VSM Haul Route Leveling)
24 | Idle Wait Waste (mins) | 13.24 | 2.648 | Forecast B cuts 80% via JIT Match-Factor
25 | Total Cycle Time / Trip | 37.24 | 10.648 | Sum of trip sub-activities
26 | Trips / Excavator / Day | 14.5005 | 50.7137 | Shift Duration / Total Cycle Time
27 | Effective Fleet Trips / Day | 29.0011 | 101.4275 | Trips per Excavator * Fleet Size
28 | Total Calendar Days | 320.6286 | 91.6771 | Total Required Trips / Effective Fleet Trips
29 | Excavator Digging Fuel (L) | 29058.0469 | 29058.0469 | Soil(0.15 L/m3) + Rock(0.40 L/m3)
30 | Tipper Hauling Fuel (L) | 46492.875 | 46492.875 | Total Trips * 15 km round trip @ 3kmpl
31 | Excavator Idle Fuel (L) | 9233.485 | 1846.697 | (Trips * Idle Mins / 60) * 4.5 L/hr stall burn
32 | Site Overhead Electricity (Tonnes) | 3.9437 | 1.1276 | Total Days * 135 kWh/day * 0.82 grid factor
33 | Total Carbon (Tonnes) | 231.1659 | 208.5532 | Converts ALL Liters to Tonnes CO2e + Electricity

## RCC
Total BUA (m²) | 2202000
Concrete Volume (m³) | 154140
Reinforcement Steel (MT) | 20698.8
Shuttering Area (m²) | 763049.0524
Number of Towers | 3
Levels per Tower | 72
Total RMC Trips (6m³) | 25690
Event Component | Forecast A (BAU Risk) | Forecast B (Lean-Optimized)
Entry & Gate Process (min) | 10 | 2.5
Queue & Parking (min) | 10 | 2.5
Discharge (6m³) (min) | 25 | 25
Clean & Exit (min) | 10 | 10
Total Cycle / Trip | 55 | 40
Site window diesel consumption/hr | 2.5 | 2.5
Diesel conumption/hr for transport distance | 5 | 5
Average transport distance for RMC plant | 15 | 15
Total diesel consumption Site Window for total trips | 58872.9167 | 42816.6667
Total diesel consumption during transport | 128450 | 128450
Total Diesel consumption | 187322.9167 | 171266.6667
Carbon emissions (t) @@ 2.68 kg/L | 502.0254 | 458.9947
Total Duration | 1584 | 1080
Total Site working hours | 9 | 9
Energy consumtion/hr | 45 | 45
Utilisation factor for Tower crane | 40% | 40%
Utilisation factor for Passenger hoist | 10% | 10%
Concrete Pump efficiency | 1.4222 | 1.4222
Steel yard efficiency | 3.5 | 3.5
Tower Cranes (3 Nos) | 256608 | 174960
Passenger Hoists (9 Nos) | 64152 | 43740
Steel Yard (On-site) | 72445.8 | 0
Concrete Pumps (3 Nos) | 219221.3333 | 0
Total Electricity | 612427.1333 | 218700
Carbon emissions (t) @0.82 kg/kWh | 502.1902 | 179.334
TOTAL RCC FOOTPRINT | 1004.2157 | 638.3287

## Finishes & MEP
Total BUA (m²) | 204570.7915
Base Plaster Area (m²) | 715997.7703
Floor Screed Area (m²) | 184113.7124
Floor Tiling Area (m²) | 184113.7124
Number of Towers | 3
Levels per Tower | 72
Total MEP Shafts (Rmts) | 3456
Event Component | Forecast A (BAU Risk) | Forecast B (Lean-Optimized)
Plaster Waste Coefficient (%) | 12.5% | 6%
Screed Waste Coefficient (%) | 8% | 4%
Tiling Waste Coefficient (%) | 10% | 4%
MEP Rework/Clash Rate (%) | 8.5% | 4%
Finishing Duration Post-RCC (Days) | 600 | 420
Material Hoist Draw (kWh/Day) | 405 | 263.25
Total Hoist Electricity (kWh) | 243000 | 110565
Plaster Waste Carbon (Tonnes) | 1342.4958 | 644.398
Screed Waste Carbon (Tonnes) | 294.5819 | 147.291
Tiling Waste Carbon (Tonnes) | 552.3411 | 220.9365
MEP Rework Carbon (Tonnes) | 11.7504 | 5.5296
Total Electricity Carbon (Tonnes) | 199.26 | 90.6633
Total Material Carbon (Tonnes) | 2201.1693 | 1018.155
Total Finishing Carbon (Tonnes) | 2400.4293 | 1108.8183